# Orion Claims Modernization

Assumptions and Dependencies | 2026-10-08 | Fictional training data

# Assumptions

A-01: AI extraction is optional for the pilot; manual document intake is an accepted fallback. Product Owner to confirm by 2026-10-16.

A-02: Pilot involves 20 claims officers; training must finish before go-live.

A-03: Policy lookup performance target is under 2 seconds per request; current observed latency is 5–8 seconds.

A-04: Compliance can review features incrementally during development, but final sign-off still requires five working days.

# Dependencies

D-01: Vendor AI extraction API delivery forecast: 2026-11-13. Owner: External Vendor.

D-02: Notification service upgrade promised by Platform Team on 2026-11-06; no confirmed commitment recorded.

D-03: UAT requires notification service upgrade and policy lookup performance remediation.

D-04: Compliance final sign-off requires five working days after feature freeze.

# Open decisions

PO to confirm pilot scope and fallback for AI extraction. Delivery Manager to reconcile final compliance review with go-live date. Platform Team to commit upgrade date.